## Slide 1: WP11: Improving the accuracy of aerosol light absorption determinations (JRA1)
Nicolas Bukowiecki, PSI (JRA1 and Task 11.1), PSI
Lucas Alados Arboledas (Task 11.2), UGR
Vassilis Amoiridis (Task 11.3), NOA
PSI, CNR, CNRS, TROPOS, NOA, JRC, UGR, KNMI, CyI, UNIVLEEDS

## Slide 2: WP11: Improving the accuracy of aerosol light absorption determinations (JRA1)
lidar
Task 11.3
UAV
and/or
babs and SSA profiling vs vertically resolved in-situ
sun/lunar photometer
In-situ
Task 11.2
24h absorption profiling:
Improvement of babs and SSA retrievals
lidar
sun/lunar photometer
light absorption by black carbon:
causes positive radiative forcing
has mainly anthropogenic sources
absorption coefficient (babs ) and mass absorption cross section (MAC) are major sources of uncertainty
Task 11.1
babs = MAC . mBC
Improvement of near-surface (ground-based and airborne)
babs and MAC measurement methods
In-situ
MAC
babs
UAV
MAC, babs , SSA
Modelling (JRA3)
Satellite retrievals
«JRAs will contribute to quantitative and qualitative improvements of the services provided by the infrastructures»

## Slide 3: Outline
General overview and status update (N. Bukowiecki)
Task 11.1: Bas Henzing (TNO): News from the ongoing Cabauw campaign
Task 11.1/2: Lucas Alados Arboledas (UGR): SLOPE campaign 2016
Task 11.3: Nikos Michalopoulos (NOA): preliminary results from the Athens smog campaign, activities during the Cyprus campaign 2016.
Taks 11.3: Jean Sciare (CyI): Recent field campaign in Cyprus (April 2016), weekly UAV monitoring activities

## Slide 4: WP11 progress and timeline
Task | Action |  | Year 1 |  | Year 2 |  | Year 3 |  | Year 4 | 
1 | Mini-aethalometer Evaluation |  |  |  |  |  |  |  |  | 
1 | In-situ closure (MAC) |  |  |  |  |  |  |  |  | 
2 | Remote sensing optimization |  |  |  |  |  |  |  |  | 
2,3 | Analysis of remote sensing studies |  |  |  |  |  |  |  |  | 
1,2,3 | In-situ and remote sensing closure |  |  |  |  |  |  |  |  | 
Field work: |  |  |  |  |  |  |  |  | Contact: | 
1,3 | Melpitz | In-situ, balloon, UAV, lidar, AOD | May / Jun 15 |  |  | Jan/ Feb 17 |  |  | Birgit Wehner | 
1 | Bologna | In-situ |  |  |  |  | Jul 2017 |  | Angela Marinoni | 
1 | Cabauw | In-situ |  |  | Sep /Oct 16 (ongoing) |  |  |  | Arnoud Apituley | 
1,3 | Athens | In-situ, balloon, UAV, lidar, AOD |  | Dec 15 – Feb 16 |  |  |  |  | Vassilis Amiridis | 
1,3 | Finokalia | In-situ, UAV, lidar, AOD |  |  |  |  | Jun 17 |  | Vassilis Amiridis | 
1,2,3 | Granada | In-situ, lidar, AOD,UAV |  |  | May / Jun 16 |  |  |  | Lucas Alados Arboledas | 
2 | Potenza | AOD, Lidar |  |  | from Apr 16 (ongoing) |  |  |  | Lucia Mona | 
1,3 | Agia Marina Xyliatou | In-situ, UAV, lidar, AOD |  |  | Apr 2016 |  |  |  | Jean Sciare | 
D11.1
CyI
D11.4
PSI/TROPOS
D11.2
UGR
D11.3
NOA
D11.5
NOA
D11.6
NOA
MS11.1
CyI
MS11.2
UGR
MS11.3
NOA
MS11.4
PSI/TROPOS
MS11.5
NOA
2015
2016
2017
2018
2019
Notes: Timeline of all activities:
Here are the milestones and deliverables, they are fixed,
We need to fill the fields down here very soon
Melpitz: ongoing
Some of the campains will be very big (especially the Athens campaign)
Time critical: Mini-aethalometer, report due in month 8
We need to be finished with field work at the end of year 3

## Slide 5: JRA1 Related Announcements
  Deliverable 11.1 is available on the ACTRIS website: «Report on validity tests of new light-weight aethalometer for airborne measurements of the light absorption coefficient at several wavelengths”
  Thanks for your contributions to TR1, Supplementary (detailed and nicely illustrated status report )is available on Actris Webpage (Documentation  Periodic Reporting  Supplement to TR1 (WP11,JRA1)
  Submission of JRA1 data to EBAS (recent Utrecht meeting): Strategy for JRA1 data submission to EBAS was discussed
  MAC-Values: Paper by Zanatta et al. is in press in Atmospheric Environment: «A European aerosol phenomenology-5: climatology of black carbon optical properties at 9 regional background sites across Europe «
  3rd ACTRIS2 General Meeting in Granada: We should again have a JRA1 splinter meeting